## Summary
Settings QA — Summary
Generated | 2026-05-03 04:47
Total findings | 99
Critical | 4
High | 21
Medium | 44
Low | 30
Findings by area |  | Findings by source
academic-calendar | 3 | CODE_REVIEW | 34
activity-log | 1 | LIVE_TEST | 15
add-ons | 2 | UX_AUDIT | 50
approval | 11
audit-logs | 6
billing | 6
campus | 7
compliance | 2
cross-cutting | 16
How to use | 1
1. Switch to the Issues tab — it's pre-filtered and sorted by severity. | 2
2. Use the dropdown arrows on each column header to filter (e.g. only Critical, only Members area). | 11
3. The 'File' column tells you exactly which file the issue is in. The 'Line' column gives the line number. | 3
4. Severity colors: red=critical (security/data-loss), orange=high (broken/silent failure), yellow=medium (UX papercut), blue=low (polish). | 4
profile | 4
school-info | 5
schools | 5
security | 2
ticket-routing | 8

## Issues
ID | Severity | Area | Type | Source | Title | Issue | Suggested fix | File | Line
CR-001 | CRITICAL | approval | multi-tenancy | CODE_REVIEW | updateApprovalRule has no org-scope check | updateApprovalRule(id, input) calls rawPrisma.approvalRule.update({ where:{id} }). ApprovalRule is not in the org-scoped Prisma extension, so an admin in org A can mutate any approval rule in org B by guessing its id. | Use prisma.approvalRule.updateMany({ where:{id, organizationId: getOrgContextId()}, data: input }) and assert count===1, OR findFirst-then-update. | src/lib/services/approvalRuleService.ts | 131
CR-002 | CRITICAL | approval | multi-tenancy | CODE_REVIEW | deleteApprovalRule has no org-scope check | rawPrisma.approvalRule.delete({where:{id}}) — same vector as CR-001. Cross-tenant rule deletion possible. | rawPrisma.approvalRule.deleteMany({ where:{id, organizationId: getOrgContextId()} }) and assert count===1. | src/lib/services/approvalRuleService.ts | 140
CR-003 | CRITICAL | approval | multi-tenancy | CODE_REVIEW | updateStep / removeStep on ApprovalFlowEntry are unscoped | updateStep and removeStep use rawPrisma.approvalFlowEntry.update/delete({where:{id}}). Bypasses the org-scoped extension; cross-tenant step manipulation possible. | Use the org-scoped prisma client (which auto-injects organizationId), or add organizationId: getOrgContextId() to every where clause. | src/lib/services/approvalRuleService.ts | 181
CR-004 | CRITICAL | approval | multi-tenancy | CODE_REVIEW | addStepToRule does not verify ruleId belongs to caller's org | addStepToRule({ruleId, ...}) blindly creates a flow entry with the supplied ruleId. Combined with CR-001 a caller in org A can attach steps to a rule in org B, planting team-membership references on the wrong tenant. | Before creating, verify rule with rawPrisma.approvalRule.findFirst({where:{id:ruleId, organizationId: getOrgContextId()}}). 404 if missing. Also verify supplied teamId belongs to caller's org. | src/lib/services/approvalRuleService.ts | 157
UX-021 | HIGH | add-ons | dead-end | UX_AUDIT | 'Enable for entire organization' button passes wrong arg in modal | When activeCampuses is empty, the button calls onToggle(mod.id, false) (currentlyEnabled=false meaning 'enable now') for what is actually a campus-scoped module. Modal closes; if API rejects org-level enable for a campus-scoped feature, no error is shown. | Disable the button when no campuses exist and show 'Add a campus first', or surface API errors back into the modal before closing it. | src/components/settings/AddOnsTab.tsx | 137
UX-007 | HIGH | approval | confirm | UX_AUDIT | Approval rule deletion has no confirm step | deleteRule(id) immediately fires DELETE — the delete button wipes a workflow rule with no confirmation. Steps and routing config are lost. | Add ConfirmDialog. For default catch-all rules, also warn that downstream events will fall through to the next matching rule. | src/components/settings/ApprovalRulesBuilder.tsx | 340
UX-023 | HIGH | approval | responsive | UX_AUDIT | Approval-rules builder uses a fixed 384px sidebar at all viewports | Two-column builder with w-96 flex-shrink-0 left panel and a flex-1 right panel. Below ~768px the right panel collapses to nothing usable. | Stack vertically below md breakpoint, or convert the left panel to a select dropdown on mobile. | src/components/settings/ApprovalRulesBuilder.tsx | 485
CR-009 | HIGH | audit-logs | permission | CODE_REVIEW | Audit logs readable by all members (SETTINGS_READ) | Audit logs include other users' email addresses, IPs, and resource changes. Gated by SETTINGS_READ, which is granted to the MEMBER default role. | Stricter permission — PERMISSIONS.ALL (super-admin) or introduce audit-logs:read granted only to admin roles. | src/app/api/settings/audit-logs/route.ts | 60
UX-003 | HIGH | billing | error | UX_AUDIT | Reactivate subscription failure is invisible | handleReactivate catch contains only '// noop — button will re-enable on error'. User clicks Reactivate, network fails, sees nothing. | Set a reactivateError state and render it next to the button, mirroring how cancelError is displayed. | src/components/settings/BillingTab.tsx | 190
UX-002 | HIGH | compliance | error | UX_AUDIT | DPA save and revoke swallow all errors | handleDpaSave and handleDpaRevoke catch blocks contain only comments — '// Keep form open on failure'. Compliance attestation silently failing is an audit/legal risk. | Add a toast or inline error banner; keep the form open AND show the error message so the user can retry. | src/components/settings/SecuritySettingsSection.tsx | 95
LIVE-001 | HIGH | cross-cutting | security | LIVE_TEST | Role 'name' accepts raw HTML/JS — stored XSS sink | POST /api/settings/roles with name='<img src=x onerror=alert(1)>' returned 201 and stored the name verbatim. The slug got sanitized but the displayable name did not. React escapes by default in {role.name}, but any future use in emails, audit-log messages, exports, or dangerouslySetInnerHTML becomes a real stored-XSS vector. | Sanitize / strip-tags name fields server-side before persisting. Apply across all user-supplied display strings (roles, teams, schools, principals, buildings, rules). | (api accepts unsanitized input)
LIVE-002 | HIGH | cross-cutting | perf | LIVE_TEST | 32 API calls fire on initial Settings page load | Single visit to /settings (Profile tab default) triggers 32 distinct API requests in network panel, including 5 calls to /api/auth/me and 3 calls to /api/auth/permissions, plus athletics/sports/teams/seasons/tournaments/games/practices/roster (none of which are settings-related but mount because of the dashboard layout). | Add a request-de-duplication layer for /api/auth/me and /api/auth/permissions (TanStack Query suspense or a single auth hook that owns the fetch). Defer athletics/dashboard fetches until those routes are visited. | src/app/settings/page.tsx + descendents
LIVE-003 | HIGH | cross-cutting | a11y | LIVE_TEST | 100+ hidden focusable elements per tab — tabs never unmount | Counted with document.querySelectorAll('[hidden] button, [hidden] input, [aria-hidden=true] button, ...'): every settings tab shows 60–115 hidden focusable elements after a few tabs have been visited. Lazy-load mounts on first visit but never tears down. Headings from previously-visited tabs (Roles, Teams, Members, Facilities) all stay in the DOM. | Either render only the active tab's component (and accept the extra mount cost on switch), or wrap inactive panels with the inert attribute so they're truly removed from focus + screen reader navigation. | src/app/settings/page.tsx | 312
LIVE-004 | HIGH | cross-cutting | a11y | LIVE_TEST | No live regions in Settings — screen readers get no save/error announcements | document.querySelectorAll('[aria-live],[role=status],[role=alert]') = 0 on every Settings tab. Toast notifications likely render outside any aria-live container, so screen reader users hear nothing when actions succeed or fail. | Wrap the global toast container in an aria-live='polite' region (and aria-live='assertive' for error toasts). Add inline status regions next to forms for save success/error. | src/app/settings/page.tsx + ChildComponents
UX-005 | HIGH | integrations | confirm | UX_AUDIT | Removing Twilio config has no confirmation | 'Remove' button calls handleRemove() directly with no ConfirmDialog. Removing Twilio destroys SMS credentials and silently breaks every notification flow that depends on it. | Wrap with a ConfirmDialog ('Remove Twilio configuration? Outbound SMS will stop immediately.'). | src/components/settings/integrations/TwilioCard.tsx | 184
UX-006 | HIGH | integrations | confirm | UX_AUDIT | Calendar Disconnect (Google/Microsoft/Planning Center) has no confirmation | Disconnect buttons in GoogleCalendarCard, MicrosoftCalendarCard, and PlanningCenterCard all execute the destructive call immediately. OAuth tokens are wiped + saved calendar selections lost. | Add a ConfirmDialog with consequences ('You'll need to reauthorize to reconnect. Saved calendars will be lost.'). | src/components/settings/integrations/GoogleCalendarCard.tsx | 291
CR-010 | HIGH | members | validation | CODE_REVIEW | Users POST has no Zod schema; weak hand-rolled validation | No email-format validation (only truthy-check). teamIds array values not verified to belong to caller's org before user creation. | Build a Zod schema (z.string().email(), enums for status/employmentType/campusScope/provisioningMode) via withAuth's schema option. Verify teamIds with prisma.team.findMany({where:{id:{in:teamIds}, organizationId:orgId}}) count check. | src/app/api/settings/users/route.ts | 120
CR-005 | HIGH | principals | auth | CODE_REVIEW | Principal POST creates User with empty passwordHash + no setup token | POST creates a User row with passwordHash:'' and status:ACTIVE. Login is blocked for empty hashes, but no setup token / welcome email is generated; the org is left with a half-provisioned user. Any future SSO/OAuth/passkey path that bypasses passwordHash would log the user in. | Use the same flow as POST /api/settings/users — generate a setup token, send the welcome email, default status to PENDING, drop the empty passwordHash. | src/app/api/settings/principals/route.ts | 193
CR-006 | HIGH | principals | permission | CODE_REVIEW | Principals search exposes PII to all org members (SETTINGS_READ) | GET /api/settings/principals?q= is gated by SETTINGS_READ which is granted to MEMBER (default role). Returns id, firstName, lastName, email, phone, jobTitle for up to 15 matches. Any active org member can scrape staff contact info. | Gate with PERMISSIONS.USERS_READ (admin only), or if regular members truly need this, return only id+name with no email/phone. | src/app/api/settings/principals/route.ts | 60
CR-007 | HIGH | principals | validation | CODE_REVIEW | Principals POST/PATCH have no Zod schema | Inputs hand-pulled from body.name/phone/phoneExt with no schema. Inconsistent with the rest of the settings surface; weakens defense. | Add a Zod schema and pass via the schema option of withAuth(). | src/app/api/settings/principals/route.ts | 100
CR-008 | HIGH | principals | permission | CODE_REVIEW | Principal POST silently picks an arbitrary role (first one returned) | prisma.role.findMany({take:1}) with no orderBy. The first role returned (often super-admin since system roles seed first) becomes the principal's role. | Resolve a specific safe role by slug (member or a dedicated principal role). Never pick the arbitrary first row. | src/app/api/settings/principals/route.ts | 175
UX-032 | HIGH | profile | confirm | UX_AUDIT | Avatar Remove has no confirmation; sits next to Change Image | handleRemoveAvatar immediately PATCHes avatar=null. Reversible by re-uploading, but the Remove button is right next to Change Image with no distinguishing color or confirmation. | Make Remove visually destructive (red text/icon), or add a quick confirm popover. | src/app/settings/ProfileTab.tsx | 209
UX-029 | HIGH | schools | onboarding | UX_AUDIT | Auto-creates 'Main Campus' silently when no campuses exist | On mount, if the org has no campuses, the resolveOrCreateCampus effect silently POSTs a 'Main Campus' record. Catch is /* silent */. User has no idea a campus was just created. | Either gate behind a visible onboarding step ('We've added a default Main Campus — rename or add more in Facilities'), or move auto-creation into org signup so it happens once with feedback. | src/components/settings/SchoolsManagement.tsx | 60
UX-001 | HIGH | security | error | UX_AUDIT | MFA toggle silently fails on error | handleMfaToggle catch is just '// Revert on failure' — no revert and no user-facing error. Admin sets a security policy thinking it saved when it didn't. | Show a toast on failure, revert mfaRequired to its prior value, surface the API error message. | src/components/settings/SecuritySettingsSection.tsx | 68
CR-011 | HIGH | ticket-routing | validation | CODE_REVIEW | Routing POST does not verify managerUserId/schoolId belong to the org | Caller-supplied managerUserId and schoolId written straight to ModuleRoutingConfig with no cross-org check. | Verify both via prisma.user.findFirst / prisma.school.findFirst against current org. 400 if missing. | src/app/api/settings/ticket-routing/route.ts | 36
UX-010 | MEDIUM | academic-calendar | a11y | UX_AUDIT | Bell schedule edit/delete actions are hover-only | Schedule Edit and Delete buttons live in a div with opacity-0 group-hover/sched:opacity-100. Touch users have no hover; keyboard-only users see actions only via :focus-within after tabbing in. Same pattern for period removal. | Show actions at low opacity by default (e.g. opacity-60) with full opacity on hover/focus, OR move them into a persistent RowActionMenu overflow. | src/components/settings/academic-calendar/BellScheduleSubTab.tsx | 301
UX-027 | MEDIUM | academic-calendar | error | UX_AUDIT | Delete mutations have no onError handler | deleteYear, deleteTerm, deleteSchedule, deleteSpecialDayMut only define onSuccess. If the API rejects (e.g., year has linked events), the user sees the dialog close with no feedback and the row still present. | Add onError that toasts the API error message. | src/components/settings/AcademicCalendarTab.tsx | 42
LIVE-008 | MEDIUM | activity-log | a11y | LIVE_TEST | Activity Log date inputs missing labels | Two date inputs in the Activity Log filter row have no <label>, aria-label, or aria-labelledby. Screen readers announce only 'date'. | Add visible labels ('From', 'To') with htmlFor wiring, or aria-label='From date' / 'To date'. | src/components/settings/AuditLogTab.tsx
CR-014 | MEDIUM | approval | validation | CODE_REVIEW | Approval flow POST/PUT do not verify teamId/assignedUserId belong to the org | Schemas validate shape but the service writes supplied teamId and assignedUserId straight to DB. Org-scoped extension prevents row from being written under another org, but a caller can still attach an assignedUser from another org. | Validate teamId and assignedUserId against caller's org via prisma.team.findFirst / prisma.user.findFirst before create/update. | src/app/api/settings/approval-flow/route.ts | 71
UX-024 | MEDIUM | approval | form | UX_AUDIT | Rule name auto-overwritten while user is typing | The school-condition onChange handler auto-rewrites the rule name to '<schoolName> Events' if the user hasn't yet set campus/category. This silently throws away whatever name the user typed if they later picked a school first. | Only auto-name when the rule is brand new (e.g., name === 'New Rule'); never overwrite a user-typed name. | src/components/settings/ApprovalRulesBuilder.tsx | 588
UX-025 | MEDIUM | approval | loading | UX_AUDIT | Optimistic rule edits with no rollback on failure | updateRule does optimistic cache update + background mutation; if mutation fails there's no rollback or visible error. Same pattern in TicketRoutingTab updateStrategy/updateCategory/updateStaffAvailability. | On mutation onError, rollback the cache to prior snapshot and surface a toast 'Failed to save — your change was reverted'. | src/components/settings/ApprovalRulesBuilder.tsx | 345
UX-039 | MEDIUM | approval | empty-state | UX_AUDIT | Right panel shows nothing when no rule is selected | Per CLAUDE.md ('No empty states that require user action to see data'), the right panel of the builder requires picking a rule first. No auto-selection of the first/default rule on load. | Default selectedRuleId to the first rule (or default-catch-all) on first render. | src/components/settings/ApprovalRulesBuilder.tsx | 575
CR-018 | MEDIUM | audit-logs | other | CODE_REVIEW | AuditLogTab triggers fetch from inside the render body | if (!fetched && !loading) { fetchLogs(1); setInitialized(true) } runs during render. Side effects + setState during render are a React anti-pattern. | Move the bootstrap fetch into a useEffect(() => { fetchLogs(1) }, []). The fetched flag is no longer needed. | src/components/settings/AuditLogTab.tsx | 283
UX-011 | MEDIUM | audit-logs | other | UX_AUDIT | Initial fetch performed during render | Calls fetchLogs(1) and setInitialized(true) inside the function body during render (not inside useEffect). Triggers a state update during render; can produce React warnings and re-runs on every render until fetched flips. | Move the initial fetch into useEffect with [] deps; or use useQuery like the rest of the codebase does. | src/components/settings/AuditLogTab.tsx | 283
UX-012 | MEDIUM | audit-logs | copy | UX_AUDIT | Action filter dropdown shows raw machine codes | ACTION_OPTIONS uses raw enum values like 'user.password-reset-complete' as labels. Users have to parse dotted, kebab-cased identifiers. | Provide human labels (e.g., 'User · Login', 'Role · Created') while keeping the value as the API code. Group by resource. | src/components/settings/AuditLogTab.tsx | 192
UX-013 | MEDIUM | audit-logs | a11y | UX_AUDIT | div with onClick used to lazy-load users for filter | Wrapping div uses onClick={fetchUsers}/onFocus={fetchUsers}. Not focusable, no role, keyboard-only users can't trigger the load. | Move the lazy-load trigger onto the FloatingDropdown's onFocus/onClick props, or fetch users on mount via useQuery. | src/components/settings/AuditLogTab.tsx | 330
UX-028 | MEDIUM | audit-logs | perf | UX_AUDIT | No virtualization on potentially large audit-log table | Table renders every row in current page. With LIMIT=25 fine, but expand-row mounts AnimatePresence div for every row; no cap on changes object size — a single big diff will lock the row. | Truncate ChangesDisplay values past N characters with a 'show full' link; consider react-virtual if page size is increased. | src/components/settings/AuditLogTab.tsx | 422
CR-023 | MEDIUM | billing | error-handling | CODE_REVIEW | Stripe error message returned to client verbatim | On Stripe failure: fail('PAYMENT_ERROR', stripeError.message). Returns Stripe internal error strings (account ids, internal codes) to the client. Same in change-plan, portal, reactivate, organization/delete. | Log Stripe error server-side; return generic message: fail('PAYMENT_ERROR', 'Failed to cancel subscription. Please try again or contact support.'). | src/app/api/settings/billing/cancel/route.ts | 92
UX-018 | MEDIUM | billing | a11y | UX_AUDIT | Org-name confirmation input has no accessible label | The 'Type organization name to confirm' input has only a placeholder, no <label> and no aria-label. Screen reader users hear 'edit text' with no purpose. | Add <label htmlFor="delete-org-confirm"> or aria-label='Type organization name to confirm'. | src/components/settings/billing/DangerZoneSection.tsx | 85
UX-019 | MEDIUM | billing | consistency | UX_AUDIT | Custom modal instead of shared ConfirmDialog | DangerZone hand-rolls a modal with its own backdrop, focus management, and z-index, while the rest of settings uses ConfirmDialog with requireText='DELETE'. Visual style and keyboard behavior diverge. | Replace with ConfirmDialog requireText={orgName} variant='danger'. Eliminates duplicated focus-trap and Escape-handling code. | src/components/settings/billing/DangerZoneSection.tsx | 60
UX-020 | MEDIUM | billing | error | UX_AUDIT | Stripe-not-configured detection conflates network errors | catch sets stripeConfigured=false on ANY fetch failure, so a transient 500 or offline state shows 'Billing Not Configured — Contact your administrator' rather than a retry option. | Only set stripeConfigured=false on the specific 'not yet configured'/SERVICE_UNAVAILABLE response codes; show generic error+retry on other failures. | src/components/settings/BillingTab.tsx | 87
CR-015 | MEDIUM | campus | validation | CODE_REVIEW | map-data PATCH has no Zod schema; no lat/lng bounds check | Manual typeof number checks, but no min/max on lat (-90..90) / lng (-180..180). Garbage coordinates land on records. | Wrap with a Zod schema (z.number().min(-90).max(90), etc.) via the schema option. | src/app/api/settings/campus/map-data/route.ts | 234
LIVE-005 | MEDIUM | campus | data-integrity | LIVE_TEST | Campus / map-data disagree about building counts | GET /api/settings/campus/buildings returns len=0 (no buildings) for the demo org, but GET /api/settings/campus/map-data returns 23 buildings. The tab and the map are sourced from different queries and don't agree. Also: 21 campuses defined but 0 rooms. | Decide which source is authoritative. Have map-data join through the buildings list, or have buildings include map-only records. Reconcile the seed/migration to match. | (data discrepancy)
UX-046 | MEDIUM | campus | architecture | UX_AUDIT | SchoolsManagement mounted invisibly to hijack imperative API | FacilitiesTab renders <SchoolsManagement> inside a hidden div purely to drive openNew via a ref. Double-mounts the component, runs duplicate effects (loadSchools, resolveOrCreateCampus), hard to reason about. | Extract the school CRUD modals into a standalone <SchoolDialogs/> component that only renders the drawers, no fetch effects, accept data as props. | src/components/settings/FacilitiesTab.tsx | 72
UX-045 | MEDIUM | compliance | form | UX_AUDIT | Remove DPA Record sits next to Save with no confirmation | 'Remove DPA Record' button placed inline with Save and Cancel and triggers handleDpaRevoke immediately. Revoking compliance attestation is significant and reversible only by re-recording. | Add ConfirmDialog with copy explaining the consequence. | src/components/settings/SecuritySettingsSection.tsx | 290
CR-019 | MEDIUM | cross-cutting | multi-tenancy | CODE_REVIEW | Interactive $transaction on org-scoped Prisma client (multi-tenancy hazard) | prisma.$transaction([...]) on the extended client. CLAUDE.md warns this can lose the extension on the inner tx and bypass org-scoping. Same pattern in roles/[id]/route.ts:97 and users/[id]/permissions/route.ts:150 affects org-scoped models like Role. | Switch batch ops to rawPrisma.$transaction([...]) with explicit organizationId in every where. For sequential writes, drop the transaction inside runWithOrgContext. | src/app/api/settings/users/[id]/route.ts | 119
LIVE-006 | MEDIUM | cross-cutting | consistency | LIVE_TEST | 'approval-config' tab is in VALID_TABS but not rendered in the nav | settings-types.ts lists 'approval-config' in VALID_TABS, but the rendered settings nav has 11 buttons (Profile, School Information, Roles, Teams, Members, Facilities, Academic Calendar, Billing, Add-ons, Integrations, Activity Log) — Approval Config is missing. URL ?tab=approval-config is accepted but lands on a blank panel. | Either add the Approval Config tab button to the workspace tab list, or remove 'approval-config' from VALID_TABS so the deep-link is rejected. | src/app/settings/settings-types.ts vs src/app/settings/page.tsx | 20
LIVE-007 | MEDIUM | cross-cutting | consistency | LIVE_TEST | Skeleton loaders only appear on Integrations and Activity Log | CLAUDE.md UI rules require skeleton loading (animate-pulse) during data fetches. Audit found .animate-pulse on the Integrations and Activity Log tabs only. Other data-loading tabs (Members, Roles, Teams, Facilities) flash a brief blank state. | Standardise: every tab that fetches on mount renders a skeleton matching the final layout shape until data resolves. | (skeleton loading inconsistent)
UX-036 | MEDIUM | cross-cutting | architecture | UX_AUDIT | localStorage-based auth headers used inconsistently with cookie auth | RolesTab, TeamsTab, MembersTab, AuditLogTab, BillingTab and several integration cards build auth headers from localStorage('auth-token'). useAuth + middleware moved to cookie-based auth. When cookie session is valid but localStorage token is missing/stale, calls 401 with no clear UI signal. | Centralize via fetchApi/getAuthHeaders helpers from @/lib/api-client and remove direct localStorage reads. | src/components/settings/RolesTab.tsx | 96
UX-048 | MEDIUM | cross-cutting | consistency | UX_AUDIT | RolesTab and TeamsTab duplicate massive reassign-on-delete logic | RolesTab (L286-379) and TeamsTab (L243-336) implement essentially the same flow: load assigned users, render bulk + per-user reassign dropdowns, gate the confirm button. ~150 lines duplicated almost verbatim. | Extract <ReassignBeforeDeleteDialog> taking { entity, entityName, assignedUsers, options, onConfirm } as a shared component. | src/components/settings/RolesTab.tsx | 50
CR-017 | MEDIUM | members | other | CODE_REVIEW | EditMemberDrawer calls setState during render | The component does prevUserId[1](user.id) and setEditForm(...) directly inside the render body whenever user.id changes. setState during render is a React rule violation that can produce 'Cannot update a component while rendering' warnings and infinite loops. | Replace with a proper useEffect(() => {...sync form...}, [user?.id]). | src/components/settings/members/EditMemberDrawer.tsx | 40
UX-014 | MEDIUM | members | other | UX_AUDIT | useState misused to derive form state during render | useState(null) → setter called during render to sync editForm when user prop changes. Classic 'derived state' anti-pattern — fragile, fires extra renders, triggers React warnings. | Use useEffect([user?.id]) to reset the form, or use the documented derive-during-render with prev-state-comparison pattern. | src/components/settings/members/EditMemberDrawer.tsx | 40
UX-015 | MEDIUM | members | form | UX_AUDIT | Invite form silently no-ops when email is blank | handleSubmit returns early on empty email with no setError. Disabled-button state hides the issue, but if the user removes the email after typing it, the form just does nothing on submit. | Use HTML required + show inline 'Email required' message; or display setError('Email is required'). | src/components/settings/members/InviteMemberDrawer.tsx | 41
UX-050 | MEDIUM | members | form | UX_AUDIT | Remove Member confirm requires typing 'DELETE' (heavy for soft-delete) | ConfirmDialog requires typing literal 'DELETE' for member removal. Members are soft-deleted and reversible by an admin via DB, so requiring DELETE-text feels heavy compared to actual destructiveness — and inconsistent with toggling member status which has no confirm. | Drop requireText for member removal (keep variant='danger' + clear message). Reserve requireText for hard-destructive ops like Delete Organization. | src/components/settings/members/MembersTab.tsx | 254
UX-004 | MEDIUM | organization | error | UX_AUDIT | Event buffer save logs to console only | Save handler only does console.error on failure and never calls setSaved(false) or surfaces the error. Admin assumes the buffer is saved when it isn't. | Track an error state and render an inline message; or use the global toast pattern. | src/components/settings/school-info/EventBufferSection.tsx | 40
UX-033 | MEDIUM | profile | confirm | UX_AUDIT | Passkey Delete has no confirmation | handleDeletePasskey is wired to the trash icon and runs immediately. Removing your last passkey when MFA is required can lock you out. | Add ConfirmDialog ('Remove this passkey? You'll need another sign-in method to access your account.'). Block deletion of the last MFA method when org-level MFA is required. | src/app/settings/ProfileTab.tsx | 1064
UX-034 | MEDIUM | profile | a11y | UX_AUDIT | Passkey rename/delete buttons missing aria-label | Icon-only buttons for Rename/Delete passkey use title= but no aria-label. Screen readers may or may not announce title; aria-label is the WAI-ARIA-recommended attribute. | Add aria-label='Rename passkey' / 'Delete passkey'. | src/app/settings/ProfileTab.tsx | 1062
LIVE-009 | MEDIUM | school-info | a11y | LIVE_TEST | School Info has unlabeled inputs and one unlabeled toggle switch | The address autocomplete (placeholder='Start typing an address...') has no label. A button with role='switch' and aria-checked='false' has no accessible name. Screen reader users can't know what the toggle controls. | Wrap inputs in <label>, add aria-label to the switch (e.g. aria-label='Enable Google Places autofill'). | src/components/settings/SchoolInfoTab.tsx
LIVE-010 | MEDIUM | school-info | a11y | LIVE_TEST | Icon-only 'Remove image' buttons use title= instead of aria-label | Two buttons with title='Remove image' have no aria-label. Screen readers may or may not announce title, and rely on aria-label per WAI-ARIA recommendations. | Switch title to aria-label, or add aria-label alongside. | (see snippet in finding)
CR-020 | MEDIUM | schools | multi-tenancy | CODE_REVIEW | School lookup uses findUnique by id with post-hoc org check | prisma.school.findUnique({where:{id}}) then check school.organizationId !== orgId. School IS auto-scoped so unique find returns null for cross-org ids, but the post-hoc check is dead code suggesting confusion. Inconsistent with buildings/rooms/spaces handlers that use findFirst. | Use prisma.school.findFirst({where:{id, organizationId:orgId}}) consistently. | src/app/api/settings/schools/[id]/route.ts | 50
CR-021 | MEDIUM | schools | consistency | CODE_REVIEW | GET /api/settings/schools?campusId=X is silently ignored by the route | Component builds /api/settings/schools?campusId=${campusId} but the route only filters on organizationId. Per-campus facilities view shows ALL org schools instead of those assigned to that campus. | Either implement campusId filtering in the route, or remove the unused param from the client. | src/components/settings/SchoolsManagement.tsx | 154
CR-022 | MEDIUM | schools | soft-delete | CODE_REVIEW | School create silently hard-deletes any soft-deleted school with the same name | POST does rawPrisma.school.deleteMany({where:{organizationId, name, deletedAt:{not:null}}}) to free up the unique constraint. Destructive op hidden behind a CREATE — orgs lose soft-deleted history when recreating same-named schools. Also bypasses audit logging. | Either keep the unique constraint partial (where: { deletedAt: null }) via raw SQL, or rename the soft-deleted record (append deletedAt to name). At minimum, audit-log the destructive deletion. | src/app/api/settings/schools/route.ts | 90
UX-030 | MEDIUM | schools | error | UX_AUDIT | Imperative openEdit fallback silently fails | openEdit() ref method: if the school isn't in local state, tries to refetch all schools and find it. Catch is empty — // silent — school not found. If the network fails or the school truly doesn't exist, drawer just never opens. | Throw or return false from openEdit so callers can show a toast 'School not found'. | src/components/settings/SchoolsManagement.tsx | 137
CR-016 | MEDIUM | security | error-handling | CODE_REVIEW | security/compliance routes mask Zod and permission errors as 500 | Both routes do not use the canonical withAuth wrapper. Their catch falls through to fail('INTERNAL_ERROR') with 500. Zod parse errors and permission denials get swallowed and reported as 500 instead of 400/403. | Migrate both routes to withAuth({permission: PERMISSIONS.ALL, schema: UpdateSchema}). The wrapper already classifies Zod, permission, and Prisma errors correctly. | src/app/api/settings/security/route.ts | 36
CR-012 | MEDIUM | ticket-routing | validation | CODE_REVIEW | Routing categories PATCH does not verify specialistUserId/fallbackUserId belong to the org | Both ids accepted from body and written straight to the routing config — could pin a user from another org. | Validate both ids with prisma.user.findFirst({where:{id, organizationId:orgId}}) before update. | src/app/api/settings/ticket-routing/categories/route.ts | 41
CR-013 | MEDIUM | ticket-routing | validation | CODE_REVIEW | Escalation POST does not verify targetUserId belongs to the org | targetUserId written to EscalationRule with no cross-org check. | prisma.user.findFirst({where:{id:targetUserId, organizationId:orgId}}) before create. | src/app/api/settings/ticket-routing/escalation/route.ts | 35
UX-008 | MEDIUM | ticket-routing | form | UX_AUDIT | SLAInput onChange prop ignored | SLAInput accepts onChange in its type signature but never uses it; only onUpdate runs. The unused prop is misleading; SLA Resolve column wires onChange={()=>{}} showing the dev knew it was no-op. | Remove the dead onChange prop, or wire it for live cache updates. | src/components/settings/TicketRoutingTab.tsx | 759
UX-009 | MEDIUM | ticket-routing | dead-end | UX_AUDIT | AddStaffButton and removeStaffMember defined but never rendered | AddStaffButton helper and removeStaffMember are declared but never invoked in the JSX. The Staff Availability section has no UI to add or remove staff — only an empty-state hint says 'Assign roles with ticket permissions to see staff here automatically.' | Either delete the dead code, or render AddStaffButton in the Staff Availability section header with a corresponding remove action per row. | src/components/settings/TicketRoutingTab.tsx | 785
UX-040 | MEDIUM | ticket-routing | form | UX_AUDIT | Manager picker shows when no config exists, hidden when config exists with non-MANAGER strategy | Condition (currentStrategy === 'MANAGER_TRIAGE' ¦¦ !currentConfig) means before any config is seeded the Triage Manager dropdown shows even though no strategy is selected — confusing. | Only show the dropdown when MANAGER_TRIAGE is the active strategy; rely on the auto-seed to populate currentConfig before rendering. | src/components/settings/TicketRoutingTab.tsx | 422
UX-026 | LOW | academic-calendar | empty-state | UX_AUDIT | Tab depends on activeSchoolId but doesn't surface 'no school selected' | Sub-tabs receive activeSchoolId from useActiveSchool. If no school is selected, schedules filter to nothing and show only 'No bell schedules configured' — user has no clue this is because of an unset filter. | Show a one-line context banner: 'Showing schedules for: <school>' with a school picker; or 'All schools' when activeSchoolId is empty. | src/components/settings/AcademicCalendarTab.tsx | 21
UX-022 | LOW | add-ons | onboarding | UX_AUDIT | Single-module registry yields a one-card Add-ons tab | Only Athletics is registered. The whole tab presents as a half-empty grid with one card and a long inline comment about features being now-core. First-time admins land on what looks like an empty/buggy screen. | Either hide the Add-ons tab from the sidebar when only one optional add-on exists, or add an explanation card alongside the Athletics card listing what's now built-in. | src/components/settings/AddOnsTab.tsx | 33
CR-029 | LOW | approval | other | CODE_REVIEW | Awaiting params inside handler when withAuth has already awaited it | const { id } = await params — params is already a plain object after withAuth awaited the dynamic-route Promise. Suggests confusion about Next.js 15 typing. | const { id } = params (no await). | src/app/api/settings/approval-rules/[id]/route.ts | 31
UX-043 | LOW | billing | consistency | UX_AUDIT | Button label varies between 'Upgrade to X' and 'Upgrade' | Plan card button cycles through 'Upgrade to Pro', 'Upgrade', 'Downgrade', 'Select Plan' depending on subscription state. Inconsistent verbosity makes plan rows visually uneven. | Standardize on '<Action> <Plan name>' (e.g., 'Upgrade to Pro', 'Downgrade to Starter'). | src/components/settings/billing/PlanComparisonSection.tsx | 113
CR-028 | LOW | campus | consistency | CODE_REVIEW | Building PATCH parses Zod manually inside handler instead of using schema option | UpdateBuildingSchema.parse(body) inside handler. If parsing throws, withAuth.classifyError turns it into a 400. Every other route uses the schema: option. Inconsistent style. | Move to withAuth(handler, { permission: ..., schema: UpdateBuildingSchema }). | src/app/api/settings/campus/buildings/[id]/route.ts | 78
CR-030 | LOW | campus | other | CODE_REVIEW | Use of any[] type for outdoor map spaces | const [outdoorMapSpaces, setOutdoorMapSpaces] = useState<any[]>([]) — explicit any violates the typescript style rule. | Define a proper interface for the outdoor space shape. | src/components/settings/CampusTab.tsx | 99
LIVE-011 | LOW | campus | data-integrity | LIVE_TEST | GET /api/settings/campus/district returns 404 'No district found' | With no district configured, the route returns 404 with NOT_FOUND. The UI must handle this without showing an error banner — confirm there's a graceful empty-state path. | Verify the Facilities tab handles 404 from this route as 'no district yet, suggest creating one' rather than a hard error. | (api shape)
UX-031 | LOW | campus | other | UX_AUDIT | CampusTab is approaching 1000 lines and should be split | Loose typing for map data and ad-hoc state inside an 800+ line file. Correlates with bugs that surface as UX problems. | Split CampusTab into ViewState reducer + CampusMapPanel + CampusListPanel; tighten types via existing ./campus/types.tsx module. | src/components/settings/CampusTab.tsx | 99
CR-024 | LOW | cross-cutting | consistency | CODE_REVIEW | Components mix cookie auth with Bearer-token auth headers | 16 settings components read localStorage.getItem('auth-token') and send Authorization: Bearer ${token} — but the actual auth path uses cookies. When a user has cookies but no localStorage token, the Bearer header is 'Bearer null' (string). | Standardise on getAuthHeaders() from @/lib/api-client (already used by ProfileTab and SchoolsManagement). | src/components/settings/BillingTab.tsx | 56
LIVE-012 | LOW | cross-cutting | consistency | LIVE_TEST | 401 from no-auth requests says 'Missing tenant context' — confusing | GET /api/settings/users without credentials returns 401 with message 'Missing tenant context'. The status code is right, but the message describes the org-scope mechanism rather than 'You're not signed in'. | Standardise on 'Authentication required' or 'Sign in to continue' for client-facing 401 messages. | (api error wording)
LIVE-013 | LOW | cross-cutting | positive | LIVE_TEST | Cross-tenant header injection IS blocked (positive) | Sending X-Organization-ID: 00000000-... to GET /api/settings/users returns the same data as the legitimate org. Confirms the middleware uses the JWT-derived orgId and ignores client-supplied X-Organization-ID. | No fix needed — document this as the intended behavior so future contributors don't mistakenly trust the header. | (positive finding)
LIVE-014 | LOW | cross-cutting | positive | LIVE_TEST | Roles + Teams CRUD round-trip works end-to-end (positive) | Create role → duplicate-detect (409) → update → delete all return 2xx with the right shape. System-role deletion correctly returns 403 FORBIDDEN. | No fix needed — keep the smoke test in CI. | (positive finding)
UX-037 | LOW | cross-cutting | perf | UX_AUDIT | Lazy-loaded tabs are kept mounted forever | Once a tab is added to visitedTabs, it stays mounted (just hidden via CSS). Switching back is instant but every visited tab keeps its data fetches/mutations alive in the background, including Activity Log polling. | For heavy tabs (AuditLog, BillingTab with Stripe portal, Approval Rules) consider unmount-when-hidden or pause queries via TanStack Query's enabled flag. | src/app/settings/page.tsx | 312
UX-044 | LOW | cross-cutting | other | UX_AUDIT | Unused imports | Plus is imported but never used in AddOnsTab. Minor — shows lint enforcement gap. | Remove unused imports; tighten ESLint config. | src/components/settings/AddOnsTab.tsx | 7
UX-047 | LOW | cross-cutting | a11y | UX_AUDIT | Reassign user dropdown lacks descriptive aria-label per row | Each per-user reassign select uses aria-label='Reassign users to role' — same string for every row. Screen-reader user hears the same label N times with no way to distinguish which user. | aria-label={`Reassign ${displayName ¦¦ user.email} to a different role`}. | src/components/settings/RolesTab.tsx | 762
CR-032 | LOW | export | permission | CODE_REVIEW | Users CSV export gated by SETTINGS_READ — too permissive for PII bulk download | Exports name, email, role, status, createdAt for all org users. Gated by SETTINGS_READ (granted to MEMBER). Members shouldn't be able to bulk-download the org member list as CSV. | Use PERMISSIONS.USERS_READ (admin only). | src/app/api/settings/export/users/route.ts | 57
CR-027 | LOW | members | perf | CODE_REVIEW | User search uses contains without DB indexes | firstName/lastName/email contains: search, mode: insensitive on every keystroke. No pg_trgm GIN index. Becomes a full table scan once orgs cross a few hundred users. | Debounce client-side now. Long term, add GIN/trigram index on User.firstName, lastName, email. | src/app/api/settings/users/route.ts | 33
CR-031 | LOW | members | consistency | CODE_REVIEW | Token / orgId pulled from localStorage at module-level scope | const token = ... localStorage.getItem('auth-token') is computed once on first render and never refreshed. If user re-authenticates in another tab, the existing tab keeps stale token in headers. | Read inside getAuthHeaders so each request reads current value, or rely on cookie auth. | src/components/settings/members/MembersTab.tsx | 56
CR-033 | LOW | members | perf | CODE_REVIEW | Bulk-PII audit log fires on every list-users request | Every page of users (limit 25 default) writes a users.read audit row. For an admin with the Members tab open + typing in search, that's one audit-log row per keystroke. Bloats the audit log; slows the table. | Throttle: only audit-log when search query changes meaningfully or page > 1. Move PII-bulk-access logging to a dedicated CSV-export endpoint. | src/app/api/settings/users/route.ts | 102
UX-016 | LOW | members | consistency | UX_AUDIT | Mixed error UI — banner for fetch error, toast for mutations | Fetch errors render an inline red banner with Retry; mutation errors show a toast. Inconsistent — users may not know where to look. RolesTab/TeamsTab use a top banner exclusively. | Pick one pattern per concern: toast for transient action results, inline banner for blocking-load failures. | src/components/settings/members/MembersTab.tsx | 197
UX-017 | LOW | members | perf | UX_AUDIT | Filter rebuilt on every keystroke without memoization | filtered recomputes on every render. Each STATUS_TAB count badge re-iterates the full users array. | Memoize counts with useMemo. | src/components/settings/members/MembersTab.tsx | 56
UX-038 | LOW | members | consistency | UX_AUDIT | Export CSV uses window.open with no auth retry path | window.open opens /api/settings/export/users in a new tab. Browsers don't send Bearer header for new tabs — only works because the API also accepts the cookie. If cookies expire user gets a raw 401 page. | Stream the CSV via a fetch with credentials, then create an object URL to download — handles 401 gracefully. | src/components/settings/members/MembersTab.tsx | 144
CR-025 | LOW | organization | permission | CODE_REVIEW | Org delete uses string match on roleName instead of permission check | if (ctx.roleName !== 'super-admin') is fragile. The route already has permission: PERMISSIONS.SETTINGS_BILLING as the wrapper-level gate, which is too weak (admin has it). | Replace with await assertCan(ctx.userId, PERMISSIONS.ALL). Tighten wrapper-level permission too. | src/app/api/settings/organization/delete/route.ts | 37
CR-026 | LOW | organization | permission | CODE_REVIEW | Organization GET readable by all members | SETTINGS_READ granted to default MEMBER role. Returns name, slug, eventBufferMinutes — exposes org slug to non-admins. Likely intentional but worth confirming. | If non-admins genuinely don't need this endpoint, gate with USERS_READ or stricter. | src/app/api/settings/organization/route.ts | 26
UX-035 | LOW | profile | other | UX_AUDIT | Initial mount fetches MFA via fetch in addition to useAuth context | ProfileTab does its own fetch('/api/auth/me') on mount bypassing the cached context already provided by useAuth. Causes an extra network call and races with the context refresh. | Read mfaEnabled from useAuth or a shared query hook. | src/app/settings/ProfileTab.tsx | 91
UX-041 | LOW | school-info | consistency | UX_AUDIT | Two save bars compete on long pages | When the form is dirty, the user sees BOTH the inline 'Save Changes' button at L522 AND the fixed bottom bar at L541. Clicking either does the same thing — but the redundancy is visual noise. | Hide the inline button when isDirty (the sticky bar takes over). | src/components/settings/SchoolInfoTab.tsx | 522
UX-042 | LOW | school-info | consistency | UX_AUDIT | Institution Type dropdown omits FAITH_BASED option | The form only offers PUBLIC/PRIVATE/CHARTER/HYBRID. But FAITH_BASED is a valid value used elsewhere. Existing FAITH_BASED orgs cannot edit this field correctly without losing their setting. | Add FAITH_BASED option (consistent with the platform's secular, multi-tenant stance — it's a category, not a religious reference). | src/components/settings/SchoolInfoTab.tsx | 411
UX-049 | LOW | school-info | copy | UX_AUDIT | Slug success message hardcodes lionheartapp.com | setSlugSuccess(`Subdomain updated to ${slugInput}.lionheartapp.com`) hardcodes the domain. NEXT_PUBLIC_PLATFORM_URL exists for this. White-label or staging instances will show wrong copy. | Read from process.env.NEXT_PUBLIC_PLATFORM_URL or NEXT_PUBLIC_APP_URL. | src/components/settings/SchoolInfoTab.tsx | 145
CR-034 | LOW | ticket-routing | perf | CODE_REVIEW | N+1 ticket-count queries in staff-availability GET | For each staff availability row, awaits rawPrisma.maintenanceTicket.count(...) inside Promise.all. N round-trips for N staff. Same N+1 in ticket-routing/dashboard/route.ts:34. | Use groupBy(['assignedToId']) once and look up counts per user from the result map. | src/app/api/settings/staff-availability/route.ts | 86
LIVE-015 | LOW | ticket-routing | other | LIVE_TEST | ticket-routing/* GETs return 400 without ?module= | GET /api/settings/ticket-routing/categories¦dashboard¦fields¦fields/library all return VALIDATION_ERROR 'module query param required (MAINTENANCE or IT)' when module is missing. This is correct API behavior, but consumers (UI components, scripts) need to know. | Document required query params on each route handler comment so consumers and AI assistants reading the code know what to send. | (api shape)